职业技能训练

Vocational Skills Training

周计划书

Weekly node report

2026年10月18日

October 18, 2026

W01 项目启动

W01 Project Kick-off

一 学生任务书

I.  Student Task Book

本周节点周检查课程目标  CO4

Weekly milestone · Weekly check · Course Objective CO4

组建能够协作的团队，留下成员、任务和版本管理的第一份记录。

Form a team that can collaborate, and leave the first record of members, tasks, and version management.

本周完成步骤

Steps to Complete This Week

- 原则上4人组队；3—5人组须由课程组批准。登记班级、姓名、学号与可投入时段。

1. Form a team of 4 as a rule; teams of 3–5 require approval from the course team. Register the class, names, student IDs, and available time slots.

2. 每人说明一项已有技能和一项需要学习的技能。设协调、实现、测试、文档等责任，允许兼任，但每人须有具体任务。

2. Each member states one existing skill and one skill to learn. Assign roles such as coordinator, implementer, tester, and documenter; concurrent roles are allowed, but everyone must have a concrete task.

3. 从原稿题库列出1个项目志愿，分别说明用户、可获得的数据或设备、预期输出和当前困难。

3. List one project preference from the original question bank, describing its users, available data or equipment, expected output, and current difficulties.

4. 约定每周一次短会、文件命名、响应方式、缺席补交和争议解决。先讨论，再由协调人记录共同决定。4. Agree on a weekly short meeting, file-naming conventions, response methods, make-up work for absences, and dispute resolution. Discuss first, then have the coordinator record the joint decisions.

5. 召开启动会并保留简要纪要。每人完成个人Log首条记录；将下一周用户调研任务分配到人。

5. Hold a kick-off meeting and keep brief minutes. Each member completes the first entry of their personal log; assign next week's user-research tasks to individuals.

先理解这两个术语

First Understand These Two Terms

Team Charter 团队章程：约定角色、协作规则和分歧处理方式。

Team Charter: an agreement on roles, collaboration rules, and how disagreements are handled.

Repository 项目仓库：保存可追踪的文档、代码与修改记录。

Repository: stores trackable documents, code, and revision history.

二 可填写模板

II.  Fillable Template

填写本页并按需要增加行。保留需求编号和原始证据编号。示例在下一页，提交前须用本团队真实内容替换填写提示。

Fill in this page and add rows as needed. Keep the requirement numbers and original evidence numbers. Examples are on the next page; before submission, replace the filling prompts with your team's real content.

专业：自动化（嵌入式）  团队编号：Team【待填】  项目名称：停车场占用监测节点

Major: Automation (Embedded)  Team No.: Team[TBD]  Project Name: Parking Space Occupancy Monitoring Node

提交人：【待填】  日期：2026-10-18  版本：v1.0

Submitted by: [TBD]  Date: 2026-10-18  Version: v1.0

成员与任务

Members and Tasks

| 姓名 学号 Name & Student ID | 角色与技能 Role & Skills | 本周任务 This Week's Tasks | 证据或版本 Evidence / Version |
| --- | --- | --- | --- |
| 成员A · 协调人 协调与文档 | 已有：电路与项目管理基础；需学：需求调研与文档规范 | 建立Git仓库、制定会议制度、登记成员信息、完成项目志愿与启动会纪要 | repo/README.md v0.1；docs/minutes_W01 |
| 成员B · 硬件与传感 传感采集 | 已有：单片机基础；需学：地磁/超声波传感器与标定 | 调研传感器是否可借用、绘制初步接线草图、搭建传感实验台 | docs/device_list_W01；sensing/wiring_v0.1 |
| 成员C · 软件与数据 通信与界面 | 已有：C/Python；需学：MQTT与嵌入式网络 | 搭建开发环境、本地部署MQTT broker、学习数据入库 | dev/env_notes；broker/conf_v0.1 |
| 成员D · 测试与文档 测试与验证 | 已有：测试基础；需学：数据分析与实验记录 | 起草个人Log模板、编写启动会议纪要、整理调研问题清单 | docs/log_template；docs/interview_questions_W01 |

项目志愿

Project Preference

| 题目编号 Item No. | 用户与场景 Users & Scenario | 资源条件 Resources | 优先顺序及理由 Priority & Rationale |
| --- | --- | --- | --- |
| 3.1（主题3 可持续交通与停车） | 用户：校园停车场管理方与开车师生/访客；痛点：找位难、空余信息不实时 | 可借地磁/超声波传感器、ESP32、本地MQTT broker、校园Wi-Fi | 第一志愿；无摄像头、隐私友好，硬件易得，技术深度适中 |

启动会议决定：

Kick-off Meeting Decisions

每周三17:00召开30分钟短会；文件命名 Team_停车场监测_YYYYMMDD；建立Git仓库（main+个人分支），文档/代码均入库；问题用Issue登记；缺席须24小时内补交纪要并认领任务；分歧由协调人组织讨论并记录，必要时请教师仲裁。
分工：A协调与文档，B硬件与传感，C软件与数据，D测试与验证。
下一周用户调研任务：A访谈停车场管理方，B/C现场观察高峰时段找位情况，D整理调研记录与证据编号。

三 自动化与计算机示例

III.  Automation & Computer Examples

以下场景、成员、编号和数值均为教学示例，不代表已开展调研、实际学生结果或学院统一验收指标。请学习写法，用真实项目替换。

The following scenarios, members, numbers, and values are teaching examples only, and do not represent conducted research, actual student results, or unified college acceptance criteria. Learn the writing style and replace them with your real project.

自动化方向示例

Automation Track Example

示例团队A有4名成员：甲负责传感采集，乙负责通信，丙负责测试，丁协调并维护文档。第一志愿A06设备柜温升监测，拟采集两个位置的温度，输出趋势与超温提示。W01只核实器件是否可借用，实际分工由学生填写。

Example Team A has 4 members: A handles sensing, B handles communication, C handles testing, D coordinates and maintains documents. First preference A06: equipment-cabinet temperature-rise monitoring, collecting temperature at two locations and outputting trends and over-temperature alerts. W01 only verifies whether components can be borrowed; the actual division of labor is filled in by students.

计算机方向示例

Computer Science Track Example

示例团队C选择C06设备巡检平台。甲负责数据结构，乙负责网页，丙负责接口测试，丁负责调研和版本管理。第一周每人各提交一项：README、用户问题清单、页面草图、测试目录说明。创建空文件不能证明开发贡献。

Example Team C chose C06: equipment inspection platform. A handles data structures, B handles web pages, C handles API testing, D handles research and version management. In week 1, each submits one item: README, user-question list, page sketch, and test-directory description. Creating an empty file does not prove development contribution.

照着示例完成的动作

Actions to Follow the Examples

先找出示例中的对象、条件、行动和证据。再把对象替换为本团队项目，把条件换为实际条件，把结果换为自己的记录。未执行的活动写“未完成”及计划，不写虚构结果。

First identify the objects, conditions, actions, and evidence in the examples. Then replace objects with your project, conditions with your actual conditions, and results with your own records. For undone activities, write "Not completed" plus a plan; do not fabricate results.

媒介与证据制作

Media & Evidence Production

图表、文档和截图用实际内容制作。截图应包含能识别版本或时间的信息，并在索引中写出来源。涉及用户的纪要、照片和数据按项目已确认的隐私措施处理。

证据路径示范  tests/TR01.xlsx 或 data/raw/run01.csv。代码采用仓库版本标识；照片和视频可作为附件或可访问链接。每条证据应标明日期、作者、版本及与哪项任务相关。

Charts, documents, and screenshots must be made from actual content. Screenshots should include information identifying the version or time, with the source noted in the index. User-related minutes, photos, and data are handled per the project's confirmed privacy measures.

Example evidence paths: tests/TR01.xlsx or data/raw/run01.csv. Code uses repository version IDs; photos and videos can be attachments or accessible links. Each piece of evidence should note the date, author, version, and related task.

本周个人反思提示

This Week's Personal Reflection Prompt

我本周建立或修改了哪个文件？版本在哪里？下一周我向谁确认什么问题？

Which file did I create or modify this week? Where is its version? Whom should I confirm what with next week?

________________________________________________________________________